## Slide 1
Capability Transfer & Handover
Engineered from Day 1 — RCPL fully owns the SSC, the modernised tech stack and the AI factory by M15; EY steps back to advisory-only thereafter.
✓
KT Milestones
Gate 1 · Shadow (~M6): RCPL observes & participates; can describe process + tooling end-to-end.
Gate 2 · Reverse-shadow (~M9–12): RCPL leads, EY supports; EY intervenes only on exception.
Gate 3 · RCPL-led (~M12–14): RCPL runs independently, EY on-call; stable for a defined period.
Gate 4 · Independent (~M15): RCPL owns fully; EY moves to advisory-only.
◑
Mixed-Team Model
40% RCPL FTE, Day 1: Named RCPL staff embedded in every pod from the start.
Fusion pods: EY expert paired with a named RCPL owner who progressively leads.
Delivery = transfer: Capability is built while the work is done, never afterwards.
Tapering footprint: EY role shifts lead → support → advisory across the waves.
⇥
Exit Readiness
SOPs & playbooks: Runbooks and process docs authored as we go, not at the end.
Tooling & platform: Ownership of the SSC, data and AI platforms transferred.
Training academy: Role-based curricula left in place for ongoing capability.
AI-factory intake: Handed over so RCPL keeps shipping new use cases post-M15.
Governance & guardrails: Control tower, model risk and guardrails run by RCPL.
What transfers to RCPL at handover — the entire operation: SSC operations across all 10 towers · modernised ERP & integrated tech stack · governed data lakehouse & executive control tower · the AI factory and its 100+ use-case pipeline · governance, responsible-AI guardrails & controls · 100% documentation (SOPs / RACI / KPIs) · hired, trained and optimised people.
→ RCPL becomes the Accountable Architect of its own System-Governed enterprise.
53
EY’s Proposal towards “Reimagining RCPL’s GBS Operations”
EY