## Slide 1
Program Handover — 3-Month Plan
Handover of the SSC & technology transformation program we delivered — its designs, platforms (SSC, data lakehouse, AI factory, ERP), governance, roadmap & capability — to RCPL’s transformation team. This is a program/ownership handover, not an operational process transition.
Month 1 · Consolidate & Prepare
Month 2 · Guided Ownership
Month 3 · Independent Run & Sign-off
EY packages the program
owners named · KT sessions
RCPL leads, EY alongside
assets & operating models transfer
RCPL owns, EY advisory
assurance · sign-off
Handover plan & governance
Program asset consolidation & documentation pack
Named RCPL owners per domain (SSC · data · AI · ERP · gov)
Knowledge-transfer sessions (design rationale, architecture, roadmap)
Access, environments & tooling ownership transfer
AI factory operating-model handover — run a live use-case cycle
Capability build — RCPL team training & certification
RCPL-led independent run — governance, roadmap & AI factory (EY on-call)
Transfer assurance, final sign-off & advisory transition
◆ Program handover sign-off
EY assets: handover playbook · program asset pack · capability & certification framework · roadmap & backlog register.
Outcome — RCPL’s transformation team owns and evolves the SSC and AI factory independently; EY moves to advisory-only.
52
EY’s Proposal towards “Reimagining RCPL’s GBS Operations”
EY